## Board
STORIES | NOT DONE | IN PROGRESS... | DONE | DROPPED
STORY # 01:
Create the Documentation
STORY # 02:
Diagrams
STORY # 02 - TASK # 02: Use Case Diagram
STORY # 02 - TASK # 02: Test Case Diagram
STORY # 01 - TASK # 01: Create Abstract
STORY # 03:
Create the user interface for admin and signup for customer
STORY # 04:
Create the source code for the admin and signup for customer
STORY # 01 - TASK # 01: Create Objective
STORY # 01 - TASK # 01: Create the Gantt Chart
STORY # 01 - TASK # 02 ERD
STORY # 02 - TASK # 03: Create signup.ui
STORY # 02 - TASK # 03: Create index.ui
STORY # 01 - TASK # 03: Create admin.ui
STORY # 02 - TASK # 04: Create signup.py
STORY # 02 - TASK # 04: Create index.py
STORY # 01 - TASK # 04: Create admin.py

## Availability Estimate
Availability Estimate
weekday | M | T | W | R | F | S | S
month | March
Resource | 2012-03-19 | 2012-03-20 | 2012-03-21 | 2012-03-22 | 2012-03-23 | 2012-03-24 | 2012-03-25
Resource | Sprint #1 | [6 empty] | Total per Resource
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Claud de Pano | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Joy Balilo | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Dan Gadia | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 0 | 0 | 0 | 0 | 0 |  |  | 0
| 0 | 0 | 0 | 0 | 0 |  |  | 0
| 0 | 0 | 0 | 0 | 0 |  |  | 0
Total per Day | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Until the end of the Sprint | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total per Sprint | 8

## Actual Spent Time
Actual Availability
weekday | F | S | S | M | T | W | R
month | September
day | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25
Resource | Sprint #1 | [6 empty] | Total per Resource
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Caud de Pano | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 6
Joy Balilo | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 6
Dan Gadia | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 3
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total per Day | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 15
Until the end of the Sprint | 7 | 0 | 0 | 0 | 0 | 0 | 0
Total per Sprint | 15

## Product BackLog
Product BackLog
Stories
State | Name | Description | Points
Done! | Documentation | The group was able to create the abstract, object, gantt chart and update it regularly.
| Diagram | The group was able to create the erd, use case diagram and test case diagram
| User Interface | In this user interface, the group create the userinterface for the admin, index and the signup.ui
| Source Code | In this source code, the group create the userinterface for the admin, index and the signup.py
Note on B2: A prioritized list of high-level requirements.
Note on B4: INVEST in stories: - Independent - Negotiable - Valuable - Estimable - Small - Testable

## 1st Sprint
|  |  |  | 24 | R | F | S | S | M | T | W
Story | Task | Category | Who | 5 | Time to finish task (person/hour)
|  |  |  | Estimate | 2018-09-20 | 2018-09-21 | 2018-09-22 | 2018-09-23 | 2018-09-24 | 2018-09-25 | 2018-09-26
Ideal Execution |  |  |  | 38 | 30.4 | 22.8 | 15.2 | 7.6 | 0 | 0 | 0
Total per Day |  |  |  | 38 | 8 | 0 | 0 | 0 | 0 | 0 | 0
Documentation | Create the Abstract |  | Claud | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Create the Objective |  | Joy | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Create the Gantt Chart |  | Joy | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Update the Gantt Chart Regularly |  | Dan | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Compile for the documentation |  | Claud | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | R | R | S | S | M | T | W
Diagram | Create the Entity Relation Diagram (ERD) |  | Claud | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | Estimate | 2018-09-20 | 2018-09-20 | 2018-09-22 | 2018-09-23 | 2018-09-24 | 2018-09-25 | 2018-09-26
| Create the Use Case Diagram |  | Joy | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Create the Test Case Diagram |  | Dan | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Ideal | 38 | 30.4 | 22.8 | 15.2 | 7.6 | 0 | 0 | 0
[12 empty] | Real | 38 | 8 | 0 | 0 | 0 | 0 | 0 | 0
User Interface | Create the admin.ui |  | Claud | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Create the index.ui |  | Joy | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Create the signup.ui |  | Dan | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Source Code | Create the admin.py |  | Claud | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Create the index.py |  | Joy | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Create the signup.py |  | Dan | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on C3: SMART Tasks: - Specific - Measurable - Achievable - Relevant - Time-Boxed