## Board
STORIES | NOT DONE | IN PROGRESS... | DONE | DROPPED
STORY # 01:
As presenter, we should create the conceptual class diagram correctly so that we will not lose track on what we are doing and we will not go back again from the start.
STORY # 02:
As the creator of the Flight ticketing page, we would like to create a customer flight status
STORY # 03:
As the creator of the Flight ticketing page, we would like to create the page wherein the customer will answer the details about their respective flight like if round trip or one way, select the origin and destination, travel dates (depart and return), how many passengers (If an adult, child, infant or senior citizen), the the flight details.
STORY # 04:
As the creator of the flight ticketing page, we would like to make the admin to see the flight details (location, departure, arrival, price, available seats) and the remarks
STORY # 01 - TASK # 01: edit the conceptual case diagram
STORY # 05:
As the creator of the flight ticketing page, we would like to admin be able to see the calendar, details about the passenger (first name, last name gender and age), and can also delete passenger.
STORY # 06:
As the creator of the flight ticketing page, we would like to make the admin be able to see the username, first name, last name, email add, address, date of birth, gender and contact number of the passenger. This will contain the one saved from the database
STORY # 07:
As the creator of the flight ticketing page, we would like connect or merge each page so that it would be working based on what we are expecting
STORY # 02 - TASK # 01: Create the customer's flight status
STORY # 03 - TASK # 01: Create the booking of flight of the customer
STORY # 04 - TASK # 01: Create the Manage flight of the admin
STORY # 05 - TASK # 04: Create the Mange Passenger section
STORY # 06 - TASK # 04: Create the Manage User
STORY # 07 - TASK # 01: Medge everything

## Availability Estimate
Availability Estimate
weekday | R | F | S | S | M | T | W
month | September
Resource | 2018-09-27 | 2018-09-28 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 2018-10-03
Resource | Sprint #2 | [6 empty] | Total per Resource
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Claud de Pano | 1 | 2 | 2 | 0 | 2 | 0 | 0 | 7
Joy Balilo | 1 | 2 | 2 | 0 | 2 | 0 | 0 | 7
Dan Gadia | 1 | 1 | 1 | 2 | 0 | 2 | 0 | 7
| 0 | 0 | 0 | 0 | 0 |  |  | 0
| 0 | 0 | 0 | 0 | 0 |  |  | 0
| 0 | 0 | 0 | 0 | 0 |  |  | 0
Total per Day | 3 | 5 | 5 | 2 | 4 | 2 | 0 | 21
Until the end of the Sprint | 18 | 13 | 8 | 6 | 2 | 0 | 0
Total per Sprint | 21

## Actual Spent Time
Actual Availability
weekday | R | F | S | S | M | T | W
month | September
day | 2018-09-27 | 2018-09-28 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 2018-10-03
Resource | Sprint #1 | [6 empty] | Total per Resource
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Caud de Pano | 1 | 2 | 2 | 0 | 2 | 0 | 0 | 7
Joy Balilo | 1 | 2 | 2 | 0 | 2 | 0 | 0 | 7
Dan Gadia | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 5
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total per Day | 3 | 5 | 5 | 2 | 4 | 0 | 0 | 19
Until the end of the Sprint | 16 | 11 | 6 | 4 | 0 | 0 | 0
Total per Sprint | 19

## Product BackLog
Product BackLog
Stories
State | Name | Description | Points
| Conceptual Case Diagram | This is the representation of the concepts drawn in a diagram showing if many to many, many to one etc
| Customer's Flight Status | Contains the
| Customer's Book a Flight | Contains if round trip or one way, select the origin and destination, travel dates (depart and return), how many passengers (If an adult, child, infant or senior citizen), the the flight details.
| Admin's Manage Flight | Contains the flight details (location, departure, arrival, price, available seats) and the remarks
| Admin's Manage Passenger | Contains the calendar, details about the passenger (first name, last name gender and age), and can also delete passenger.
| Admin's Manage Users | Contains username, first name, last name, email add, address, date of birth, gender and contact number of the passenger. This will contain the one saved from the database.
| Merging | connects the login section to flight ticketing.
Note on B2: A prioritized list of high-level requirements.
Note on B4: INVEST in stories: - Independent - Negotiable - Valuable - Estimable - Small - Testable

## 2nd Sprint
|  |  |  | 24 | R | F | S | S | M | T | W
Story | Task | Category | Who | 5 | Time to finish task (person/hour)
|  |  |  | Estimate | 2018-09-27 | 2018-09-28 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 2018-10-03
Ideal Execution |  |  |  | 21 | 16.8 | 12.6 | 8.4 | 4.2 | 1.7764e-15 | 0 | 0
Total per Day |  |  |  | 21 | 3 | 5 | 5 | 2 | 4 | 0 | 0
CCD | Create the conceptual class diagram |  | Claud | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| that contains one-to-one, one-to-many, |  | Joy | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| many-to-one or many-to-many. |  | Dan | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | R | R | S | S | M | T | W
Customer's Flight Status | Create the customer.ui |  | Claud | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 |  | Estimate | 2018-09-27 | 2018-09-20 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 2018-10-03
| Create the customer.py |  | Claud | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
[12 empty] | Ideal | 21 | 16.8 | 12.6 | 8.4 | 4.2 | 1.7764e-15 | 0 | 0
[12 empty] | Real | 21 | 3 | 5 | 5 | 2 | 4 | 0 | 0
Customer's Book a Flight | Create the FlightTicketing.ui |  | Joy | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0
| Create the FlightTicketing.py |  | Joy | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Manage Flights | Create the departure.ui |  | Claud | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0
| Create the departure.py |  | Claud | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Manage Passengers | Create the return.ui |  | Joy | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0
| Create the return.py |  | Joy | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Manage Users | Create the payment.ui |  | Dan | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0
| Create the payment.py |  | Dan | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0
Merging | Merge from login to payment |  | Dan | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0
Note on C3: SMART Tasks: - Specific - Measurable - Achievable - Relevant - Time-Boxed