## Board
STORIES | NOT DONE | IN PROGRESS... | DONE | DROPPED
STORY # 01:
As the creator of the program, we would like to Install visual studio code and db browser for sqlite to see the better compilation of codes.
STORY # 02:
As the creator of the program we would like to work or study for the partial codes for the database of the project
STORY # 03:
As the creator of the Flight ticketing page, we would like to create on the dbhelper and the db initialize.
STORY # 04:
As the creator of the flight ticketing page, we would like to create the controller and model for the project.
STORY # 01 - TASK # 01: Install visual studio code and db browser for sqlite.
STORY # 05:
As the creator of the flight ticketing page, we would like to test our program so we will know that errors of our program and to make the customer's request be achieved.
STORY # 06:
As the creator of the flight ticketing page, we would like to polish our work so tat it will flow smooth as expected.
STORY # 02 - TASK # 01: Start partial codes for the database.
STORY # 03 - TASK # 01: Create the dbhelper and db initialize code.
STORY # 04 - TASK # 01: Create the controller and model.
STORY # 05 - TASK # 01: Create the testing
STORY # 06 - TASK # 01: polishing

## Availability Estimate
Availability Estimate
weekday | R | F | S | S | M | T | W
month | October
Resource | 2018-10-04 | 2018-10-05 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-09 | 2018-10-10
Resource | Sprint #2 | [6 empty] | Total per Resource
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Claud de Pano | 1 | 1 | 3 | 0 | 2 | 0 | 0 | 7
Joy Balilo | 1 | 3 | 1 | 0 | 2 | 0 | 0 | 7
Dan Gadia | 1 | 1 | 0 | 3 | 0 | 2 | 0 | 7
| 0 | 0 | 0 | 0 | 0 |  |  | 0
| 0 | 0 | 0 | 0 | 0 |  |  | 0
| 0 | 0 | 0 | 0 | 0 |  |  | 0
Total per Day | 3 | 5 | 4 | 3 | 4 | 2 | 0 | 21
Until the end of the Sprint | 18 | 13 | 9 | 6 | 2 | 0 | 0
Total per Sprint | 21

## Actual Spent Time
Actual Availability
weekday | R | F | S | S | M | T | W
month | September
day | 2018-10-04 | 2018-10-05 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-09 | 2018-10-10
Resource | Sprint #1 | [6 empty] | Total per Resource
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Caud de Pano | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2
Joy Balilo | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 4
Dan Gadia | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total per Day | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 8
Until the end of the Sprint | 5 | 0 | 0 | 0 | 0 | 0 | 0
Total per Sprint | 8

## Product BackLog
Product BackLog
Stories
State | Name | Description | Points
| Install Visual Studio Code and db browser for Sqlite | This visual studio code is the one used to see the better view of the compilation of the codes, while for the db browser for sqlite contains the database where customers do sign in their details like their first name, last name, birth date and the likes.
| DBHelper | Contains data data source, sql connection and cursor, the result, data, data table and if it has error.
| DBInitialize | Contains the user table, flight table, location table, country table, city table, passenger table and the payment table.
| Controller | Imports from he system from the views of signup window, admin window, customer window, login window, and the model imports users, flights, passengers and payments.
| Model | Contains the database from the dbhelper. It has the user class, flight class, passenger class and payment class.
| Tesing | Contains the printed data and data table
| Polishing | Makes sure that the program works properly.
Note on B2: A prioritized list of high-level requirements.
Note on B4: INVEST in stories: - Independent - Negotiable - Valuable - Estimable - Small - Testable

## 2nd Sprint
|  |  |  | 24 | R | F | S | S | M | T | W
Story | Task | Category | Who | 5 | Time to finish task (person/hour)
|  |  |  | Estimate | 2018-10-04 | 2018-10-05 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-09 | 2018-10-10
Ideal Execution |  |  |  | 21 | 16.8 | 12.6 | 8.4 | 4.2 | 1.7764e-15 | 0 | 0
Total per Day |  |  |  | 21 | 3 | 5 | 0 | 0 | 0 | 0 | 0
Install VSC and DB Browser for SQLite | Install the visual studio code |  | Claud | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| and |  | Joy | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| DB Browser for SQLite |  | Dan | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | R | R | S | S | M | T | W
DB Helper | data source |  | Claud | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | Estimate | 2018-10-04 | 2018-09-20 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-09 | 2018-10-10
| sql connection and cursor |  | Claud | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| result, data and data table |  | Claud | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ideal | 21 | 16.8 | 12.6 | 8.4 | 4.2 | 1.7764e-15 | 0 | 0
| if it has error |  | Claud | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Real | 21 | 3 | 5 | 0 | 0 | 0 | 0 | 0
DB Initialize | create user table and flight table |  | Joy | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| create the location table and country table |  | Joy | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| create the city table |  | Joy | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| create the passenger and payment table |  | Joy | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Models | create the user class |  | Dan | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| create the flight class |  | Dan | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| create the passenger and payment class |  | Dan | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Controlers | Import qtcore, qtgui and qtwidgets from pyqt5 |  | Joy | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| import signup, admin, customer and login window from views |  | Claud | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| import users, flights, passengers and payments from models |  | Claud | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Testing | print the data and data table |  | Joy | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Polishing | Polish everything |  | Dan | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on C3: SMART Tasks: - Specific - Measurable - Achievable - Relevant - Time-Boxed